|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **2.3 Ensure academic standards are maintained in all distance learning environments.** |  | **Goal I** |  |  |
|  ***MEASURES*:** |  |  |  |  |
| 2.3.1 Establish an Online Learning Committee by Spring 2018. | Associate Academic Dean/OLC ad-hoc committee |  | Limited | **Completed, spring 2018** |
| 2.3.2 Create Online Teaching Handbook by Spring 2020. | Online Learning Committee |  | Limited | **In Process as of May 2019** |
| 2.3.3 Create and formalize policies for online education by Spring 2019 | Online Learning Committee |  | Limited | **In Process as of May 2019** |
| 2.3.4 Provide faculty training and resources in ‘best practices’ of online course design and instruction on an ongoing basis. | Academic Dean, Associate Academic Dean, Grant Coordinator |  | Moderate | 1. **Essentials of Online Course Design – 3 week workshop offered 2X year**
2. **Plan to add two more levels in AY1920**
 |
| 2.3.5 Implement a quality assurance system for fully and hybrid online courses by Spring 2021. | Online Learning Committee & Department Chairs |  | Moderate | 1. **In process on first step of choosing a Course Design Checklist, May 2019**
 |
| 2.3.6 Ensure parity for support of online students, faculty, and courses with on-campus students, faculty, and students by Fall 2021.  | Academic Dean, Associate Academic Dean, Grant Coordinator  |  | Moderate |  |